## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
1 | As a website visitor, I want to search for hospital based on code and procedure. | Sprint 1 | C. Jones | 2022-07-05 |  | No | No | High | In Progress | 24 | No
| 1. Get the input entered by the user and remove unwanted characters. | " " | " " | 2022-07-05 | 2022-07-05 | Yes | Yes | Medium | Complete | 8 | Yes | This section is for the drop-down list
| 2. Search the database using the input entered by the user. | " " | " " | 2022-07-06 | 2022-07-07 | Yes | Yes | Medium | Complete | 16 | Yes | Yes | High | Complete
| 3. Sort the result with the cheapest hospital starting first. | " " | " " | 2022-07-08 | 2022-07-09 | Yes | Yes | Medium | Complete | 0 | Yes | No | Medium | In Progress
2 | As a website visitor, I want to see the hospital details based on what I search. | Sprint 1 | [10 empty] | Low | Not Started
| 1. Format the data received from the database. | " "
| 2. Display the formatted data to the user. | " "
3 | As a website visitor, I want to see the hospital details based on the cheapest option. | Sprint 1
| 1. Receive the data from the database and format based on the cheapest option. | " "
| 2. Display the result to the user. | " "
4 | As a website visitor, I want to see the hospital details based on the closest option. | Sprint 1
| 1. Receive the data from the database and format based on the closest option. | " "
| 2. Display the result to the user. | " "
5 | As a website visitor, I want to see the hospital details based on the best option. | Sprint 1
| 1. Receive the data from the database and format based on the best option which is calculated based on the highest score given by the cost and distance of the hospital. | " "
| 2. Display the result to the user. | " "
6 | As a developer, I will need to learn SSIS which is SQL Server Integration Process. With SSIS I will be able to update or modify the data set. | Sprint 1
7 | As a website visitor, I want to add my location to the website. | Sprint 2
| 1. Get the current location of the user. | " "
| 2. Ask the user for its location. | " "
| 3. Validate the location and apply it to the maps. | " "
8 | As a developer, I want to integrate a functional map. | Sprint 2
| 1. Add the maps into the website. | " "
| 2. Pin location. | " "
| 3. Calculate distance. | " "
9 | As a website visitor, I want to see the list of hospitals based on the range of cost entered in the search box | Sprint 2
| 1. Search the database with the input entered by the user. | " "
| 2. Implement price filter. | " "
| 3. Display the result received back to the user. | " "
10 | As a website visitor, I want to see the list of hospitals based on the distance entered in the search box | Sprint 2
| 1. Search the database with the input entered by the user. | " "
| 2. Implement distance filter. | " "
| 3. Display the result received back to the user. | " "
11 | As a website visitor, I want to see the hospital details based on the closest option. | Sprint 2
| 1. Calculate the distance based on the user's location. | " "
| 2. Display the result to the user. | " "
12 | As a website visitor, I want to see the hospital details based on the best option. | Sprint 2
| 1. Calculate the best score based on the user's location and cost of the hospital. | " "
| 2. Display the result to the user. | " "
13 | As a developer, I want to update or modify the data set. | Sprint 2
| 1. Access the location where the database is located and replace it with the new or modified data. | " "
14 | As a website visitor, I want to see the maps filters and results beside the data. | Sprint 2
| 1. Format website to accommodate the map filters and data on the same page. | " "
15 | As a website visitor, I want a separate search for code and procedure. | Sprint 2
| 1. Format the website to include two search box, one for code and one for procedure. | " "
16 | As a developer, I want to perform general refactoring. | Sprint 2
17 | As a developer, I will need to learn machine learning. With machine learning I will be able to analyse the input entered by the user. | Sprint

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.