## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | Dependency | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 As a website visitor, I want to add my location to the website. | 20 |  |  | In review
1. Get the current location of the user. |  | Topu + Henry + Arnav |  | In review | 4 | 0 | 2 | 2 | 0 | 0 | 0
2. Ask the user for its location. |  | Topu + Henry + Arnav |  | In review | 11 | 0 | 5 | 6 | 0 | 0 | 0
3. Validate the location and apply it to the maps. |  | Topu + Henry + Arnav |  | In review | 5 | 0 | 0 | 5 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2 As a developer, I want to integrate a functional map. | 10
1. Add the maps into the website. |  | Topu + Henry + Arnav | User Story 1 | In review | 4 | 0 | 3 | 1 | 0 | 0 | 0
2. Pin location. |  | Topu + Henry + Arnav |  | In Development | 4 | 0 | 0 | 1 | 0 | 0 | 0
3. Calculate distance. |  | Topu + Henry + Arnav |  | In review | 2 | 0 | 0 | 2 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 As a website visitor, I want to see the list of hospitals based on the range of cost entered in the search box | 3 |  |  | In review
1. Implement price filter. |  | Anthony + Afzal + Matthew |  | In review | 2 | 0 | 0 | 0 | 0 | 0 | 0
2. Display the result received back to the user. |  | Anthony + Afzal + Matthew |  | In review | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #4 As a website visitor, I want to see the list of hospitals based on the distance entered in the search box | 8 |  |  | In Development
2. Implement distance filter. |  | Anthony + Afzal + Matthew |  | In Development | 3 | 0 | 0 | 0 | 0 | 0 | 0
3. Display the result received back to the user. |  | Anthony + Afzal + Matthew |  | In Development | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #5 As a website visitor, I want to see the hospital details based on the closest option. | 3 |  |  | Closed
1. Calculate the distance based on the user's location. |  | Anthony + Afzal + Matthew | User Story 1 & 2 | Closed | 1 | 0 | 0 | 0 | 0 | 0 | 0
2. Display the result to the user. |  | Anthony + Afzal + Matthew |  | Closed | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #6 As a website visitor, I want to see the hospital details based on the best option. | 3 |  |  | Closed
1. Calculate the best score based on the user's location and cost of the hospital. |  | Anthony + Afzal + Matthew | User Story 1, 2 & 5 | Closed | 1 | 0 | 0 | 0 | 0 | 0 | 0
2. Display the result to the user. |  | Anthony + Afzal + Matthew |  | Closed | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #7 As a developer, I want to update or modify the data set. | 1 |  |  | Closed
1. Access the location where the database is located and replace it with the new or modified data. |  | Anthony |  | Closed | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0
User Story #8 As a website visitor, I want to see the maps filters and results beside the data. | 3 |  |  | In development
1. Format website to accommodate the map filters and data on the same page. |  | Anthony + Afzal + Matthew |  | In development | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #9 As a website visitor, I want a separate search for code and procedure. | 3 |  |  | In Review
1. Format the website to include two search box, one for code and one for procedure with each search box returning entries |  | Anthony + Afzal + Matthew |  | In Review | 1 | 0 | 1 | 0 | 0 | 0 | 0
2. validate the two search boxes to disallow a search when both search boxes are not null |  | Anthony + Afzal + Matthew |  | In Review | 3 | 0 | 2 | 0 | 0 | 0 | 0
3. Modify layout to have search bars side by side with buttons underneath |  | Anthony + Afzal + Matthew |  | In Review | 1 | 0 | 1 | 0 | 0 | 0 | 0
4. Validate the two search boxes to limit the input to only be either the code or description. |  | Anthony + Afzal + Matthew |  | In Review | 2 | 0 | 4 | 0 | 0 | 0 | 0
User Story #10 As a developer, I want to perform general refactoring. | 3
Task |  | Everyone | All of the user stories | To Do | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | To Do | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  |  | 51 | 0.5 | 18.5 | 17 | 0 | 0 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.