## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 40
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) |  |  |  |  | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | Task Balance | Percentage Completed
Issue 1 = Search | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 100%
Issue 2 = Display | 13 | 5 | 2 | 3 | 3 | 0 | 0 | 100%
Issue 3 = Cheapest | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100%
Issue 4 = Closest | 4 | 0 | 3 | 0 | 0 | 0 | 1 | 75%
Issue 5 = Best | 8 | 0 | 1 | 5 | 0 | 0 | 2 | 75%
Issue 6 = Learning SSIS | 5 | 2 | 1 | 0 | 0 | 0 | 2 | 60%
Effort Remaining | 40 | 28 | 16 | 8 | 5 | #N/A | 5 | 87.5%
Ideal Trend | 40 | 32 | 24 | 16 | 8 | 0
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days