## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 54
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) |  |  |  |  | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | Task Balance | Percentage Completed
User Story 1 | 20 | 0 | 9 | 11 | 0 | 0 | 0 | 100%
User Story 2 | 10 | 0 | 0 | 8 | 8 | 0 | -6 | 160%
User Story 3 | 3 | 0 | 0 | 2 | 0 | 0 | 1 | 66.67%
User Story 4 | 4 | 0 | 0 | 0 | 2 | 0 | 2 | 50%
User Story 5 | 2 | 0 | 0 | 3 | 4 | 0 | -5 | 350%
User Story 6 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 100%
User Story 7 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 100%
User Story 8 | 2 | 0 | 0 | 0 | 4 | 2 | -4 | 300%
User Story 9 | 7 | 0 | 9 | 0 | 0 | 0 | -2 | 128.6%
User Story 10 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 33.33%
Effort Remaining | 54 | #N/A | 3 | -21 | -35 | #N/A | -12 | 122.2%
Ideal Trend | 54 | 43.2 | 32.4 | 21.6 | 10.8 | 3.5527e-15
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days